GRANITE SIGNAL SYSTEMS

White Label Implementation Plan

Custom Domain, Logo & Login Branding on HighLevel

An Isolated, Standalone Plan — Companion to the Master Execution Plan V2.0

Prepared August 21, 2026

# Scope of This Plan

This document is scoped narrowly to White Labeling — replacing HighLevel's own branding with Granite Signal Systems' custom domain, logo, and login screen so clients see “Granite Signal Systems,” not HighLevel. It does not cover SaaS Mode (self-serve client billing, automated sub-account creation, and rebilling with markup) — a separate, higher-tier HighLevel feature set that the Master Execution Plan's Section 7 explicitly defers (“Do NOT buy at launch”). White Labeling and SaaS Mode are frequently bundled together in HighLevel's own marketing, but they solve different problems and sit at different price points. This plan treats them as distinct decisions.

⚠  Current HighLevel pricing confirms Basic White Label (custom login domain, logo, brand colors, branded email notifications) requires the Unlimited plan at $297/month. The Starter plan ($97/month) does not include white-label features. SaaS Mode requires Agency Pro at $497/month and is out of scope here.

# A. Cost Overview

## One-Time / Setup Costs

| Item | Estimated Cost | Notes |
| --- | --- | --- |
| Domain registration (if new) | $12–$20/year | Skip if Granite already owns a working domain; use a subdomain of it (e.g., app.granitesignalsystems.com) |
| Logo & brand identity | $0–$800 | DIY (Canva/Figma) at low end; freelance designer for a logo + basic style guide at the higher end. Full brand agency ($1,500+) is not warranted at this stage |
| Public marketing website build | $0–$500 | Can be built inside HighLevel's own included website/funnel builder at effectively $0 marginal cost; budget applies only if building externally (e.g., WordPress) or hiring a designer |
| Terms & Conditions / Privacy Policy drafting | $50–$800 | Template-based service (e.g., Termly) at the low end; attorney-reviewed at the high end. Bundle with the counsel review already required under Section 3 of the Master Plan rather than engaging separately |
| Trademark clearance search | $0–$600 | A DIY USPTO/NH search costs nothing but time; a professional clearance search reduces the risk of investing in a brand identity tied to a name that isn't actually clear |
| Founder/staff setup time | 15–25 hours | DNS configuration, platform branding, testing, and QA — the dominant real cost at this stage is time, not cash |
| TOTAL ESTIMATED ONE-TIME COST | $65–$1,900 | Wide range reflects DIY vs. outsourced branding choices; the platform mechanics themselves (DNS, SSL, login branding) carry no direct fee beyond the plan upgrade below |

## Recurring Monthly Costs

| Item | Monthly Cost | Required? | Notes |
| --- | --- | --- | --- |
| HighLevel Unlimited plan | $297 | Required | Replaces the $97 Starter plan — the net incremental cost of white-labeling is $200/month over the current baseline. Also removes the 3-sub-account ceiling as a side benefit |
| Domain renewal (amortized) | ~$1–$2 | Required | Annual renewal spread monthly |
| White label mobile app | $497 | Optional — defer | A separate add-on; without it, HighLevel's mobile app still shows HighLevel branding. Not recommended for this initial phase — revisit once mobile presence is a proven client need |
| Branded Client Portal App | $49/sub-account | Optional — defer | Gives individual clients their own branded portal; a later-phase upsell, not a launch requirement |
| Dedicated email IPs | $59/IP | Optional — defer | Improves email deliverability at higher volume; unnecessary at current client counts |
| WordPress hosting (if used) | from $10/site | Optional | Only if the public marketing site is built outside HighLevel's own builder |
| ESTIMATED REQUIRED RECURRING COST | ~$298–$300/mo |  | Reflects only the required items; optional add-ons are deferred by design |

SSL certificates and DNS-level branding carry no additional fee — HighLevel auto-provisions SSL on the white-label domain at no extra cost once the CNAME record is verified.

# B. Steps and Process Flow — From Branding the Website Onward

This is a sequential, roughly 5-week process. Each step depends on the one before it — do not skip ahead to DNS configuration before the brand identity and name clearance are settled.

## Step 1 — Confirm Brand Foundation (Week 1–2)

- Confirm the Granite Signal Systems name is actually clear — complete the NH QuickStart search and trademark search flagged in the Master Plan's opening checklist, before investing further in branded assets.

- Finalize the logo, color palette, typography, and a short tagline.

- Write a one-page internal brand style guide so every touchpoint — website, login screen, email signatures — stays visually consistent.

⚠  Do not proceed to paid branding investment (designer, website build) until the name is confirmed clear. Rebranding after a rejected trademark or a name conflict wastes this entire budget.

## Step 2 — Domain & DNS Setup (Week 2)

- Secure the primary marketing domain if not already owned (e.g., granitesignalsystems.com).

- Decide the branded login subdomain — recommended: app.granitesignalsystems.com (a subdomain, not the root domain, so any HighLevel-side issue never takes down the main marketing site).

- Set up DNS management through a reliable provider (Cloudflare is commonly recommended for fast propagation and control — note the specific configuration caveat in Step 5).

## Step 3 — Build the Public Marketing Website (Week 2–3)

- Build the outward-facing site explaining Granite's services — this can be done inside HighLevel's own included website/funnel builder at no additional platform cost.

- Publish Terms & Conditions and Privacy Policy pages — required later for the white-label login configuration.

- Include a contact/demo-request form — this becomes the first live proof point of Granite's own lead-response system in action.

## Step 4 — Upgrade the HighLevel Plan (Week 3)

- Upgrade from Starter to the Unlimited plan ($297/month) — this is the plan tier that unlocks white-label branding.

- Confirm unlimited sub-accounts are now available.

## Step 5 — Configure the White-Label Domain (Week 3–4)

- In HighLevel: Agency Settings → Company → Whitelabel Domain.

- Enter the chosen subdomain (app.granitesignalsystems.com).

- Add the CNAME record HighLevel provides to the domain's DNS settings at the registrar/DNS provider.

- Wait for DNS propagation (typically 15–60 minutes; budget up to 24–48 hours in worst-case scenarios) and automatic SSL issuance.

⚠  If using Cloudflare: set the CNAME record to “DNS only” (grey cloud, not the orange proxy). Leaving Cloudflare's proxy active is the most common cause of SSL provisioning failure on HighLevel white-label domains.

## Step 6 — Platform Branding (Week 4)

- Upload the Granite Signal Systems logo in Agency/Company Settings.

- Apply brand colors throughout the interface.

- Add the Terms & Conditions and Privacy Policy URLs published in Step 3.

- Verify no visible HighLevel name/branding remains anywhere in the client-facing experience.

## Step 7 — Branded Email Sending Domain (Week 4)

- Configure SPF, DKIM, and DMARC records so automated client-facing emails send from a Granite-branded address, not a generic or HighLevel-default one.

- Send test emails and confirm they land in the inbox (not spam) with correct sender branding.

## Step 8 — Internal QA (Week 4–5)

- Create a test sub-account and walk through the entire experience as a client would — login screen, logo, dashboard, no visible HighLevel references.

- Check for the common failure points documented by HighLevel support: duplicate DNS A-records on the root domain, SSL protocol errors, and stale propagation.

- Fix any issues found before touching a real client account.

## Step 9 — Client Rollout (Week 5+)

- Onboard new clients through the branded experience going forward as standard practice.

- If any clients are already live on the unbranded setup, plan their migration deliberately — exporting and manually recreating automations can be required, since field mappings do not always carry over cleanly.

## Step 10 — Marketing Activation (Week 5+, overlapping)

- Roll the new brand identity across every outward-facing touchpoint — website, email signatures, sales collateral, social profiles.

- Update the demo script and screen-recording (Section 15G/15I of the Master Plan) to show the newly branded interface.

# C. How Granite Will Market the Brand

White labeling is fundamentally a trust and professionalism signal — it does not replace the existing local B2B sales machine already defined in Section 15 of the Master Plan, and it should not be treated as a new marketing channel in its own right. What it does is strengthen the credibility of the sales motion already underway.

## How the Brand Investment Gets Used

- Every client-facing touchpoint — login screens, automated emails, booking pages — now carries Granite's own branding, functioning as a distributed brand impression across every homeowner interaction on every client's account.

- The 12-minute demo (Section 15G) and the 2-minute screen-recording tactic (Section 15I) should be re-recorded on the newly branded interface, reinforcing the positioning line from Section 2: “you are paying for a managed system, not access to AI.”

- The public marketing website becomes a credible, professional front door for prospects doing their own research after an initial email or call — particularly relevant for the more skeptical Tier 2/3 prospect.

- Local SEO on the new marketing domain, targeted at NH-specific contractor search terms, is a low-cost complement once the site exists — not a launch requirement.

- Once the first branded client is live, their case study/testimonial can be captured using the branded interface, reinforcing brand consistency in future sales materials.

## What This Plan Deliberately Avoids

- No mass-market paid brand advertising. Section 15 of the Master Plan is explicit that early sales stay manual, local, and precise — white labeling supports that motion, it doesn't replace it.

- No overstated “we built this software” claims. Market Granite as “our own managed platform” or “the system we built and manage for you” — both true and defensible — rather than implying proprietary software engineering that didn't happen. A sophisticated Tier 3 prospect's IT staff can and sometimes will investigate the underlying infrastructure.

# D. Initial Resource Requirements

This initiative does not require new hires beyond what the existing staffing roadmap already anticipates. It is scoped as founder-led work, optionally supplemented by one freelance contractor for design.

| Resource | Role in This Plan | Est. Time / Cost |
| --- | --- | --- |
| Founder | Owns DNS configuration, platform branding, QA testing, and final sign-off. This is not delegated to offshore staff at this stage — it touches core account security and brand identity decisions. | 15–25 hours over ~5 weeks |
| Freelance logo/brand designer (optional) | One-time logo and basic style guide, if not handled in-house via Canva/Figma. | $150–$800, one-time |
| Attorney (existing relationship) | Reviews Terms & Conditions/Privacy Policy language and confirms name-clearance status — bundle into the counsel review already required under Section 3 rather than a separate engagement. | Marginal — bundled review |
| Generalist VA (if already hired per the staffing roadmap) | Can assist with content population on the marketing website and basic QA checklist execution, but should not be given DNS or agency-settings access. | A few hours, if available |

The HighLevel-trained offshore technician role defined in the broader staffing roadmap is not needed for this initiative. White labeling is a one-time foundational setup, not an ongoing per-client build task — it fits naturally into the founder's own Phase 0–Phase 1 workload.

# E. Risk Matrix — White Label Initiative

Likelihood and impact are relative to Granite's current stage — a planning tool, not a formal actuarial assessment.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Business name not yet legally clear when branding investment begins | Medium | Severe (wasted brand spend, forced rebrand) | Complete the NH QuickStart and trademark search before committing to a logo, domain, or paid design work — sequencing already built into Step 1 |
| DNS misconfiguration causes login downtime or SSL errors across ALL clients simultaneously | Medium | High (single point of failure spans every client, not just one) | Test thoroughly in Step 8 before rollout; use a subdomain (not root domain) to isolate marketing site DNS from the app login domain |
| Cloudflare proxy or duplicate DNS A-records block SSL provisioning | Medium–High | Medium (delays launch, temporary access issues) | Follow the documented “DNS only” Cloudflare setting; check for duplicate root A-records as the first troubleshooting step, per HighLevel's own support guidance |
| Increased fixed monthly cost ($200/mo delta for Unlimited) taken on before client volume justifies it | Medium | Medium (cash flow pressure pre-revenue or early-stage) | Consider timing the upgrade to coincide with approaching the 3-client Starter ceiling, rather than defaulting to it immediately, per Section 7's general “don't buy at launch” discipline |
| Existing/legacy clients require migration; automations don't carry over cleanly | Low–Medium (depends on current client count) | Medium–High (support burden, possible configuration errors) | Plan migrations deliberately per client rather than in bulk; verify each automation manually post-migration rather than assuming a clean transfer |
| Mobile app still shows HighLevel branding (separate $497/mo add-on required for full mobile white-label) | High (by default, if not purchased) | Low–Medium (inconsistent brand experience if clients expect full mobile branding) | Don't market a “fully white-labeled mobile experience” unless the add-on is purchased; set expectations accurately in the meantime |
| Reputational risk if “Granite's own platform” positioning is perceived as misleading once a sophisticated client's IT staff investigates the underlying infrastructure | Medium (Tier 3 specifically) | Medium (trust/credibility) | Market as “our own managed platform,” never as proprietary software Granite engineered from scratch — an honest framing that's still commercially strong |
| Add-on cost creep (branded mobile app, dedicated email IPs, premium support) purchased prematurely | Medium | Medium (margin erosion) | Treat every optional add-on in Section A as deferred by default; revisit only when a specific, proven need arises |
| Domain/brand spoofing or phishing targeting the new branded domain as it gains recognition | Low initially, rising over time | Medium–High (client trust, compliance exposure) | Enforce DMARC properly (Step 7), monitor for look-alike domain registrations as the brand grows |
| Marketing materials update inconsistently with the actual platform branding (old logo/colors lingering in some materials) | Low–Medium | Low (polish/consistency issue) | Use the one-page brand style guide from Step 1 as the single source of truth when updating any client-facing material |

# F. Additional Considerations

## Sequencing Relative to Overall Growth

The Master Execution Plan's Section 7 discipline — don't buy the Unlimited plan until the 3-sub-account Starter ceiling is actually hit — is a reasonable default. White labeling should be triggered by one of two deliberate paths: (1) the natural point where client count forces the Unlimited upgrade anyway, at which point white-labeling is essentially free to add on top, or (2) an earlier, conscious decision to prioritize brand credibility — for example, ahead of pursuing a Tier 2/3 prospect where a polished, branded platform materially strengthens the pitch. Path 2 is a legitimate choice but should be made deliberately, not by default, since it accelerates a $200/month fixed cost ahead of the client volume that would otherwise justify it.

## Boundary With SaaS Mode

This plan stops at branding. It does not include SaaS Mode's self-serve client billing, automated sub-account creation on signup, or rebilling with markup — all Agency Pro ($497/month) features. Those solve a different problem (turning Granite into a self-service software resale business) than what was asked for here (clients simply seeing Granite's brand instead of HighLevel's). If self-serve billing becomes a priority later, it should be evaluated as its own separate decision, not bundled into this branding initiative by default.

## Recommended Domain Structure

Keep the white-label login domain as a subdomain (app.granitesignalsystems.com) of the primary marketing domain, rather than the root domain itself. This isolates any HighLevel-side incident from taking down the public marketing website's DNS, and is the structure HighLevel's own documentation and most implementation guides recommend.

This plan is a companion to, not a replacement for, the Master Execution Plan V2.0 and the Tiered Service Framework. Costs and setup times should be reconfirmed against HighLevel's current pricing page and support documentation immediately before execution, as both can change.